## project_backlog
ID | IID | Title | Description | Type | URL | State | Confidential | Locked | Milestone | Labels | Author | Author Username | Assignee | Assignee Username | Created At (UTC) | Updated At (UTC)
737 | 11 | Implement user's profile view/display page | '- Build the page where users see their own profile information with their actual name displayed. - Show approval status and assigned reviewer unique ID (once approved). - Display "Pending Approval" message if waiting. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/11 | Open | No | No | Sprint 1 | Frontend I | Ryan Douglas | rcdouglas | Colleen Grimshaw | crgrimshaw | 2026-01-31 01:01 | 2026-02-18 16:56
738 | 12 | Create profile editing interface | '- Build the form that allows users to edit their demographic information and profile description. - Pre-populate with existing data, show their name in the header, and handle update submissions. - Display unique ID but make it read-only (cannot be edited). | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/12 | Open | No | No | Sprint 1 | Frontend I | Ryan Douglas | rcdouglas | Colleen Grimshaw | crgrimshaw | 2026-01-31 01:02 | 2026-02-17 21:00
739 | 13 | Build user profile dashboard | '- Create the main profile management page showing user's actual name, profile status, edit button, and notifications (approved/rejected). - Display reviewer unique ID prominently once approved with explanation: "This is how others will see you on reviews." | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/13 | Open | No | No | Sprint 1 | Frontend I | Ryan Douglas | rcdouglas | Colleen Grimshaw | crgrimshaw | 2026-01-31 01:04 | 2026-02-19 20:17
744 | 18 | Coordinate reviewer unique ID generation system across backend/frontend | '- Design and implement the unique ID system (format: sequential numbers, UUIDs, or custom. It‚Äôs up to you guys). - This ID serves as the primary key in the database. - Ensure backend generates IDs at profile creation and frontend displays them consistently: user's own name when logged in viewing their content, but unique ID when viewing others' content. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/18 | Open | No | No | Sprint 1 | Full Stack | Ryan Douglas | rcdouglas | Daniel Szurek | djszurek | 2026-01-31 01:15 | 2026-02-23 03:35
745 | 19 | Test complete profile creation ‚Üí approval workflow | '- Manually test the full user journey: create account ‚Üí fill profile form (including name) ‚Üí submit ‚Üí admin sees name + unique ID in queue ‚Üí admin approves ‚Üí user sees their name on their profile but knows others see only their unique ID. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/19 | Open | No | No | Sprint 1 | Full Stack | Ryan Douglas | rcdouglas | Daniel Szurek | djszurek | 2026-01-31 01:16 | 2026-01-31 01:16
747 | 21 | Create end-to-end tests for critical paths | '- Write automated tests (or detailed test scripts) for: profile creation with unique ID generation, admin approval, profile editing, and proper display of name vs. unique ID based on logged-in state. Catch integration bugs early. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/21 | Open | No | No | Sprint 1 | Full Stack | Ryan Douglas | rcdouglas | Daniel Szurek | djszurek | 2026-01-31 01:17 | 2026-01-31 01:17
750 | 24 | Resources Page | Build main /resources page with 3 cards (First Steps, Tutorials, News/Featured) Page doesn't exist. Needs new route, layout with card grid, links to sub-sections | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/24 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:02 | 2026-02-22 18:06
751 | 25 | Resources: First Steps sub-page | Content page for new users getting started | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/25 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:03 | 2026-02-22 18:03
752 | 26 | Resources: Tutorials sub-page | Tutorials content, possibly linking to external sites (e.g., Abilio) | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/26 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:04 | 2026-02-22 18:04
753 | 27 | Resources: News/Featured sub-page | Blog-style posts similar to featured reviews on homepage | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/27 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:05 | 2026-02-22 18:05
754 | 28 | Navbar: Add "Resources" tab | Add to menuItems array in Navbar.tsx with dropdown for sub-pages Done after completing of resources page | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/28 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:06 | 2026-02-22 18:06
755 | 29 | Navbar: Remove "Browse All Profiles" from Reviewer Profiles dropdown | Tab to view all listed reviewers deemed not needed for general use of website. Don't need it in the reviewer profiles drop down. Navbar.tsx:39: remove this menu item | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/29 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:08 | 2026-02-22 18:09
756 | 30 | Navbar: Move "Find Similar Profiles" into Reviews dropdown | Move from Reviewer Profiles dropdown -> Reviews dropdown Leads into removing the Reviewer Profiles tab | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/30 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:09 | 2026-02-22 18:09
757 | 31 | Navbar: Show profile picture (top-right) when user is logged in | Currently always shows "Login" button (Navbar.tsx:164-170). Needs conditional rendering using useAuth() to show avatar when authenticated, Login button when not | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/31 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:11 | 2026-02-22 18:13
758 | 32 | Profile dropdown: clicking profile pic opens profile dashboard | Dropdown menu with links to profile/dashboard/logout Implemented after the profile picture | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/32 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:12 | 2026-02-22 18:12
759 | 33 | Guest -> Login user workflow | Login page exists but needs integration with the full workflow: guest browses -> clicks login -> views reviews (read-only, no posting) If user is an approved reviewer, they are able to submit reviews. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/33 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:14 | 2026-02-22 18:14
760 | 34 | "Save reviews for later" feature | Users should be able to bookmark/save reviews. Needs frontend UI (save button on review cards, saved reviews page) | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/34 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:16 | 2026-02-22 18:16
761 | 35 | Review detail page: connect to real API data | reviews/[category]/[slug].tsx exists but backend returns hardcoded JSON | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/35 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:16 | 2026-02-22 18:18
762 | 36 | Reviews listing page: connect to real API data | reviews/index.tsx exists but backend returns mock data | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/36 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:17 | 2026-02-22 18:17
763 | 37 | Reviewer profile page: display reviewer anonymously | Backend logic exists in reviewerController.ts:71-93 but frontend may not handle anonymous vs. owner views properly | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/37 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:18 | 2026-02-22 18:18
764 | 38 | Remove /reviewer-profiles browse-all page | Tab to view all reviewers not needed by general users. Remove or repurpose reviewer-profiles/index.tsx | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/38 | Open | No | No |  | Frontend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:20 | 2026-02-22 18:20
765 | 39 | Remove demo/mock login fallback from AuthContext | AuthContext.tsx:88-104 ‚Äî hardcoded admin@example.com / password123 bypass must be removed before production | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/39 | Open | No | No |  | Frontend I, Security | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:21 | 2026-02-22 19:44
766 | 40 | Admin: "Create new admin" UI | Admin should be able to promote users or create admin accounts. No UI currently exists | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/40 | Open | No | No |  | Frontend II | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:22 | 2026-02-22 18:22
767 | 41 | Admin: "Purge reviewers" functionality (UI) | Admin should be able to delete reviewer profiles. UI for delete with confirmation | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/41 | Open | No | No |  | Frontend II | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:23 | 2026-02-22 18:23
768 | 42 | Admin: "Purge reviews" functionality (UI) | Admin should be able to delete/archive reviews. UI for delete with confirmation | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/42 | Open | No | No |  | Frontend II | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:24 | 2026-02-22 18:24
769 | 43 | Admin: Resources tab CRUD (create/edit/post) | Admin should be able to create, edit, and publish resource posts (First Steps, Tutorials, News). Needs admin pages + RichTextEditor integration | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/43 | Open | No | No |  | Frontend II | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:25 | 2026-02-22 18:25
770 | 44 | Implement Review Controller | reviewController.ts is empty. All review routes in reviewRoutes.ts return hardcoded JSON. Need getReviews, getReview, getReviewsByCategory with real Mongoose queries | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/44 | Open | No | No |  | Backend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:29 | 2026-02-22 18:29
771 | 45 | Implement Product Controller | productController.ts is empty. All product routes in productRoutes.ts return hardcoded JSON | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/45 | Open | No | No |  | Backend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:29 | 2026-02-22 18:29
772 | 46 | Review routes: wire up to controller + add auth middleware | reviewRoutes.ts has inline handlers with mock data. Needs to import controller functions and add protect middleware on POST/PUT/DELETE | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/46 | Open | No | No |  | Backend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:34 | 2026-02-22 18:34
773 | 47 | Product routes: wire up to controller + add auth middleware | productRoutes.ts has inline handlers with mock data. Needs to import controller functions and add protect middleware on POST/PUT/DELETE | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/47 | Open | No | No |  | Backend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:35 | 2026-02-22 18:35
774 | 48 | "Save reviews for later": backend model + API | Need a SavedReview model (or field on User) + endpoints: POST /api/users/saved-reviews, GET /api/users/saved-reviews, DELETE /api/users/saved-reviews/:id | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/48 | Open | No | No |  | Backend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:37 | 2026-02-22 18:37
775 | 49 | Resources: backend model + CRUD API | Need a Resource model (title, content, category [first-steps/tutorials/news], author, publishDate, status) + routes: GET /api/resources, GET /api/resources/:slug | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/49 | Open | No | No |  | Backend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:37 | 2026-02-22 18:37
776 | 50 | Review writing + submission workflow | Reviewer writes review -> status = draft -> submits for approval -> admin approves -> status = published. Controller logic needed | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/50 | Open | No | No |  | Backend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:38 | 2026-02-22 18:38
777 | 51 | Reviewer profile: update model to match frontend ReviewerProfileData interface | Frontend api.ts:129-155 sends reviewerType, disabilityTypes, mobilityAids, ageRange, driverStatus, etc. Backend ReviewerProfile.ts has height (Number), weight (Number), impairments[] These schemas don't match | Issue | https://ecocar-gitlab.ua.edu/evc/mc-website/-/issues/51 | Open | No | No |  | Backend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:39 | 2026-02-22 18:39
778 | 52 | Email service: implement password reset emails | sendEmail function is referenced but not fully implemented. Needs nodemailer config with real SMTP credentials | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/52 | Open | No | No |  | Backend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:41 | 2026-02-22 18:41
779 | 53 | Image upload for reviews | Review model has images[] field but no upload endpoint or file storage (multer/S3/etc.) | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/53 | Open | No | No |  | Backend I | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:42 | 2026-02-22 18:42
780 | 54 | Admin: create new admin endpoint | POST /api/admin/users or PUT /api/admin/users/:id/role needs admin auth + role assignment | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/54 | Open | No | No |  | Backend II | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:53 | 2026-02-22 18:53
781 | 55 | Admin: delete reviewer profile endpoint | DELETE /api/admin/profiles/:id admin route to purge reviewer profiles. adminRoutes.ts doesn't have this | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/55 | Open | No | No |  | Backend II | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:53 | 2026-02-22 18:53
782 | 56 | Admin: delete/archive review endpoint | DELETE /api/admin/reviews/:id or PATCH /api/admin/reviews/:id/archive | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/56 | Open | No | No |  | Backend II | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:54 | 2026-02-22 18:54
783 | 57 | Admin: review approval/rejection endpoints | Profile approve/reject exists in adminController.ts. Review approve/reject does not exist; the Review model has status: draft/published/archived but no admin controller to change it | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/57 | Open | No | No |  | Backend II | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:55 | 2026-02-22 18:55
784 | 58 | Admin: Resources CRUD endpoints | POST/PUT/DELETE /api/admin/resources admin can create, edit, and delete resource posts | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/58 | Open | No | No |  | Backend II | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:55 | 2026-02-22 18:55
785 | 59 | Add authorize('admin') to review write routes | POST/PUT/DELETE /api/reviews/* currently have zero auth middleware, anyone can create/update/delete reviews | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/59 | Open | No | No |  | Backend II, Security | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:56 | 2026-02-22 19:44
786 | 60 | Add authorize('admin') to product write routes | POST/PUT/DELETE /api/products/* currently have zero auth middleware, anyone can create/update/delete reviews | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/60 | Open | No | No |  | Backend II, Security | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:56 | 2026-02-22 19:46
787 | 61 | Review writing -> approval -> posting pipeline (end-to-end) | Reviewer writes on frontend -> saves draft (backend) -> submits for review -> admin sees in queue -> approves/rejects -> published review appears on site. Touches Review model, controller, admin controller, frontend review form, admin review dashboard | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/61 | Open | No | No |  | Full Stack | Ryan Douglas | rcdouglas |  |  | 2026-02-22 18:58 | 2026-02-22 18:58
788 | 62 | Resources page (end-to-end) | Model + API + admin CRUD UI + public-facing pages with cards | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/62 | Open | No | No |  | Full Stack | Ryan Douglas | rcdouglas |  |  | 2026-02-22 19:42 | 2026-02-22 19:42
789 | 63 | User "save review" feature (end-to-end) | Backend model + API + frontend save button + saved reviews page | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/63 | Open | No | No |  | Full Stack | Ryan Douglas | rcdouglas |  |  | 2026-02-22 19:42 | 2026-02-22 19:42
790 | 64 | Login workflow (end-to-end) | Register -> create reviewer profile (pending) -> admin approves -> reviewer can write reviews. Frontend profile creation + backend approval + frontend gating on reviewer status | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/64 | Open | No | No |  | Full Stack | Ryan Douglas | rcdouglas |  |  | 2026-02-22 19:43 | 2026-02-22 19:43
791 | 65 | Enforce strong JWT secret in production | auth.ts:38 falls back to 'default_secret'. Should fail startup if JWT_SECRET is not set in production | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/65 | Open | No | No |  | Security | Ryan Douglas | rcdouglas |  |  | 2026-02-22 19:46 | 2026-02-22 19:46
792 | 66 | Add request validation to review/product routes | Auth routes have express-validator checks; review and product routes have none | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/66 | Open | No | No |  | Security | Ryan Douglas | rcdouglas |  |  | 2026-02-22 19:46 | 2026-02-22 19:46
793 | 67 | Enable rate limiting | express-rate-limit is installed but not applied anywhere. Login and registration are vulnerable to brute force | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/67 | Open | No | No |  | Security | Ryan Douglas | rcdouglas |  |  | 2026-02-22 19:47 | 2026-02-22 19:47
794 | 68 | Remove/secure .env credentials | server/.env contains MONGO_URI with plaintext password. Ensure .env is gitignored and prod uses environment variables | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/68 | Open | No | No |  | Security | Ryan Douglas | rcdouglas |  |  | 2026-02-22 19:47 | 2026-02-22 19:47
795 | 69 | Add HTTPS enforcement for production | Nginx config has SSL mount points but no certificates configured | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/69 | Open | No | No |  | Security | Ryan Douglas | rcdouglas |  |  | 2026-02-22 19:48 | 2026-02-22 19:48
796 | 70 | Fix auth middleware missing return | auth.ts:61-63 the if (!token) block doesn't return, so the response can be sent after next() was already called in the try block | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/70 | Open | No | No |  | Security | Ryan Douglas | rcdouglas |  |  | 2026-02-22 19:49 | 2026-02-22 19:49
797 | 71 | Sanitize req.body spread on review/product creation | Routes like POST /api/reviews do ...req.body directly ‚Äî allows mass assignment of any field. Should allowlist fields | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/71 | Open | No | No |  | Security | Ryan Douglas | rcdouglas |  |  | 2026-02-22 19:49 | 2026-02-22 19:49
798 | 72 | Add input sanitization for XSS | Review content field accepts raw HTML (rich text). Needs server-side sanitization (e.g., dompurify or sanitize-html) before storing | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/72 | Open | No | No |  | Security | Ryan Douglas | rcdouglas |  |  | 2026-02-22 19:50 | 2026-02-22 19:50