## evc-mc-website_work_items_2026-
ID | IID | Title | Description | Type | URL | State | Confidential | Locked | Milestone | Labels | Author | Author Username | Assignee | Assignee Username | Created At (UTC) | Updated At (UTC) | Closed At (UTC)
727 | 1 | Implement admin approval/rejection endpoints | '- Create POST /api/admin/profiles/:id/approve and /api/admin/profiles/:id/reject endpoints that update profile status. - Profile unique ID should already exist from creation. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/1 | Closed | No | No | Sprint 1 | Backend II | Ryan Douglas | rcdouglas | Ryan Douglas | rcdouglas | 2026-01-30 17:16 | 2026-02-17 02:19 | 2026-02-17 02:19
728 | 2 | Build admin profile review/listing endpoints | '- Create GET /api/admin/profiles endpoint that returns all pending profiles with full information (name, demographics, unique ID) for admin review queue. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/2 | Closed | No | No | Sprint 1 | Backend II | Ryan Douglas | rcdouglas | Ryan Douglas | rcdouglas | 2026-01-30 17:17 | 2026-02-17 02:18 | 2026-02-17 02:18
729 | 3 | Create admin dashboard data queries (pending profiles, statistics) | '- Write MongoDB aggregation queries to count pending/approved/rejected profiles, show recent activity, and provide admin dashboard metrics. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/3 | Closed | No | No | Sprint 1 | Backend II | Ryan Douglas | rcdouglas | Ryan Douglas | rcdouglas | 2026-01-30 17:17 | 2026-02-17 02:18 | 2026-02-17 02:18
730 | 4 | Implement profile status management logic | '- Build the state machine logic for profile statuses: pending ‚Üí approved/rejected - Implement an initial testing framework that will validate changes made | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/4 | Closed | No | No | Sprint 1 | Backend II | Ryan Douglas | rcdouglas | Ryan Douglas | rcdouglas | 2026-01-30 17:18 | 2026-02-13 00:56 | 2026-02-13 00:56
731 | 5 | Implement authorize function in server/src/middleware/auth.ts | '- Function to check user roles (admin, reviewer, editor) - Required for admin-only routes | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/5 | Closed | No | No | Sprint 1 | Backend II | Ryan Douglas | rcdouglas | Ryan Douglas | rcdouglas | 2026-01-30 17:18 | 2026-02-13 02:51 | 2026-02-13 02:51
732 | 6 | Implement reviewer profile creation endpoint | '- Create POST /api/profiles endpoint that accepts user demographic data (name, height, weight, disability type, mobility aids, etc.) and stores it in MongoDB with "pending" status. - Generate reviewer unique ID to use as primary key. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/6 | Closed | No | No | Sprint 1 | Backend I | Ryan Douglas | rcdouglas | Samuel Wisnoff | slwisnoff | 2026-01-31 00:56 | 2026-02-20 18:50 | 2026-02-20 18:50
733 | 7 | Build profile read/view endpoints for users | '- Create GET /api/profiles/:id and GET /api/profiles/me endpoints so users can view their own profile and see their approval status. - Return both name and unique ID so frontend can display appropriately based on who's logged in. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/7 | Closed | No | No | Sprint 1 | Backend I | Ryan Douglas | rcdouglas | Samuel Wisnoff | slwisnoff | 2026-01-31 00:57 | 2026-02-20 18:51 | 2026-02-20 18:51
734 | 8 | Implement profile update/edit endpoint | '- Create PUT /api/profiles/:id endpoint allowing users to edit their demographic information and profile description. - Ensure unique ID never changes. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/8 | Closed | No | No | Sprint 1 | Backend I | Ryan Douglas | rcdouglas | Samuel Wisnoff | slwisnoff | 2026-01-31 00:57 | 2026-02-20 18:49 | 2026-02-20 18:49
735 | 9 | Create database queries for user's own profile management | '- Write MongoDB queries to fetch, filter, and update profile data for the logged-in user. - Include queries that return reviewer unique ID for linking to reviews later. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/9 | Closed | No | No | Sprint 1 | Backend I | Ryan Douglas | rcdouglas | Samuel Wisnoff | slwisnoff | 2026-01-31 00:58 | 2026-02-20 18:50 | 2026-02-20 18:50
736 | 10 | Build reviewer profile creation form with all demographic fields | '- Create the multi-step form where users enter name, height, weight, disability type, mobility aids used, profile description, etc. Include validation and clear labels. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/10 | Closed | No | No | Sprint 1 | Frontend I | Ryan Douglas | rcdouglas | Colleen Grimshaw | crgrimshaw | 2026-01-31 01:01 | 2026-02-20 19:00 | 2026-02-20 19:00
737 | 11 | Implement user's profile view/display page | '- Build the page where users see their own profile information with their actual name displayed. - Show approval status and assigned reviewer unique ID (once approved). - Display "Pending Approval" message if waiting. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/11 | Open | No | No | Sprint 1 | Frontend I | Ryan Douglas | rcdouglas | Colleen Grimshaw | crgrimshaw | 2026-01-31 01:01 | 2026-02-18 16:56
738 | 12 | Create profile editing interface | '- Build the form that allows users to edit their demographic information and profile description. - Pre-populate with existing data, show their name in the header, and handle update submissions. - Display unique ID but make it read-only (cannot be edited). | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/12 | Open | No | No | Sprint 1 | Frontend I | Ryan Douglas | rcdouglas | Colleen Grimshaw | crgrimshaw | 2026-01-31 01:02 | 2026-02-17 21:00
739 | 13 | Build user profile dashboard | '- Create the main profile management page showing user's actual name, profile status, edit button, and notifications (approved/rejected). - Display reviewer unique ID prominently once approved with explanation: "This is how others will see you on reviews." | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/13 | Open | No | No | Sprint 1 | Frontend I | Ryan Douglas | rcdouglas | Colleen Grimshaw | crgrimshaw | 2026-01-31 01:04 | 2026-02-19 20:17
740 | 14 | Build admin dashboard for profile approval queue | '- Create the admin view showing all pending reviewer profiles in a table/card format. - Display both the user's actual name AND their unique ID (format: "Jane Doe Reviewer #12345") so admins can identify profiles. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/14 | Closed | No | No | Sprint 1 | Frontend II | Ryan Douglas | rcdouglas | Nicholas Yeager | nmyeager | 2026-01-31 01:05 | 2026-02-17 04:29 | 2026-02-17 04:29
741 | 15 | Implement profile approval/rejection interface | '- Build the detail view where admins see full profile information including real name, unique ID, and all demographics. - Have clear Approve/Reject buttons with confirmation modals to prevent accidents. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/15 | Closed | No | No | Sprint 1 | Frontend II | Ryan Douglas | rcdouglas | Nicholas Yeager | nmyeager | 2026-01-31 01:06 | 2026-02-17 04:30 | 2026-02-17 04:30
742 | 16 | Create admin profile management views | '- Build pages for admins to view all profiles (pending, approved, rejected) with filtering and search capabilities. - Show both names and unique IDs in listings. - Display profile statistics and recent activity. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/16 | Closed | No | No | Sprint 1 | Frontend II | Ryan Douglas | rcdouglas | Nicholas Yeager | nmyeager | 2026-01-31 01:08 | 2026-02-17 19:55 | 2026-02-17 19:55
743 | 17 | Build admin statistics display | '- Create dashboard widgets showing total profiles, approval rate, pending count, and recent approvals/rejections. - Use charts/graphs if time permits. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/17 | Closed | No | No | Sprint 1 | Frontend II | Ryan Douglas | rcdouglas | Nicholas Yeager | nmyeager | 2026-01-31 01:09 | 2026-02-17 04:30 | 2026-02-17 04:30
744 | 18 | Coordinate reviewer unique ID generation system across backend/frontend | '- Design and implement the unique ID system (format: sequential numbers, UUIDs, or custom. It‚Äôs up to you guys). - This ID serves as the primary key in the database. - Ensure backend generates IDs at profile creation and frontend displays them consistently: user's own name when logged in viewing their content, but unique ID when viewing others' content. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/18 | Open | No | No | Sprint 1 | Full Stack | Ryan Douglas | rcdouglas | Daniel Szurek | djszurek | 2026-01-31 01:15 | 2026-02-23 03:35
745 | 19 | Test complete profile creation ‚Üí approval workflow | '- Manually test the full user journey: create account ‚Üí fill profile form (including name) ‚Üí submit ‚Üí admin sees name + unique ID in queue ‚Üí admin approves ‚Üí user sees their name on their profile but knows others see only their unique ID. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/19 | Open | No | No | Sprint 1 | Full Stack | Ryan Douglas | rcdouglas | Daniel Szurek | djszurek | 2026-01-31 01:16 | 2026-01-31 01:16
746 | 20 | Implement profile search/filter across user and admin views | '- Build search functionality allowing admins to filter profiles by name, unique ID, status, date, or demographics. Later enable users to search for reviewers with similar characteristics (showing only unique IDs, not names). | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/20 | Closed | No | No | Sprint 1 | Full Stack | Ryan Douglas | rcdouglas | Daniel Szurek | djszurek | 2026-01-31 01:17 | 2026-02-23 03:27 | 2026-02-23 03:27
747 | 21 | Create end-to-end tests for critical paths | '- Write automated tests (or detailed test scripts) for: profile creation with unique ID generation, admin approval, profile editing, and proper display of name vs. unique ID based on logged-in state. Catch integration bugs early. | Task | https://ecocar-gitlab.ua.edu/evc/mc-website/-/work_items/21 | Open | No | No | Sprint 1 | Full Stack | Ryan Douglas | rcdouglas | Daniel Szurek | djszurek | 2026-01-31 01:17 | 2026-01-31 01:17
748 | 22 | Local Server Instance Failure | Running the Server locally is currently not possible, this is in part due to outdated package incompatibilities, and a lack of a Server .env file to point the Mongodb connection to the localhost. | Issue | https://ecocar-gitlab.ua.edu/evc/mc-website/-/issues/22 | Closed | No | No | Sprint 1 |  | Ryan Douglas | rcdouglas | Ryan Douglas | rcdouglas | 2026-02-10 16:20 | 2026-02-10 20:28 | 2026-02-10 20:28
749 | 23 | Analytics button, application review routing, minor admin tweaks | '- Remove approval percentage from main dash, can be in main analytics page but does not need to be in quick view. - Adjust routing behavior for 'Review Applications" button in pending approvals card to behave in the same manner as the other buttons on the page - Not large issue, just ensuring consistent behavior across pages and buttons | Issue | https://ecocar-gitlab.ua.edu/evc/mc-website/-/issues/23 | Closed | No | No | Sprint 1 | Frontend II | Daniel Szurek | djszurek | Nicholas Yeager | nmyeager | 2026-02-17 03:09 | 2026-02-18 16:40 | 2026-02-18 16:40